## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Intial project setup including Maven Configuration, JDK Installation , package structuring , and revision of java fundamentals required for the banking simulation project | MUST HAVE | NA | Shilpa Sina,Shivani,Navya N, Uppari Mounika , Riya Kumari | Completed
Sprint 1 | Sprint 1 | US-02 | Design and implementation of Account model and repository layer to manage account details and balances | MUST HAVE | US-01 | Shivani | Completed
Sprint 2 | Sprint 2 | US-03 | Implementation of AccountService to support account creation, balance initialization, and account retrieval operations | MUST HAVE | US-02 | Shilpa Sina | Completed
Sprint 2 | Sprint 2 | US-04 | Development of TransactionService for deposit, withdrawal, and fund transfer with proper validations and business rules | MUST HAVE | US-03 | Navya N | Completed
Sprint 3 | Sprint 3 | US-05 | Creation of custom exception handling for invalid amount, insufficient balance, and account not found scenarios | MUST HAVE | US-04 | Uppari Mounika | Completed
Sprint 3 | Sprint 3 | US-06 | Implementation of alert service to track low balance conditions and trigger notifications using utility classes | SHOULD HAVE | US-03 | Riya Kumari | Completed
Sprint 4 | Sprint 4 | US-07 | Development of user interface to perform banking operations and display transaction results | COULD HAVE | US-04 | Shivani , Navya N | Completed
Sprint 4 | Sprint 4 | US-08 | Integrate frontend UI with backend APIs and perform end-to-end testing | SHOULD HAVE | US-07 | Navya N | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 4 | 5 | 6 | 9 | 9
SPRINT 1 BACKLOG
US-01 | T-01 | Install JDK, Maven and configure development environment | 2025-12-01 | 2025-12-01 | Navya N | Setup | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Create Maven project and base package structure | 2025-12-02 | 2025-12-02 | Navya N | Development | Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Revise Java fundamentals required for project | 2025-12-03 | 2025-12-03 | Navya N | Learning | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Design Account model class | 2025-12-04 | 2025-12-04 | Shivani | Development | Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-05 | Implement AccountRepository logic | 2025-12-05 | 2025-12-06 | Shivani | Development | Completed | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-06 | Unit testing for account creation | 2025-12-08 | 2025-12-08 | Shivani | Testing | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-03 | T-07 | Implement account creation service logic | 2025-12-09 | 2025-12-10 | Navya N | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-04 | T-08 | Implement deposit functionality | 2025-12-11 | 2025-12-11 | Navya N | Development | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0
US-04 | T-09 | Implement withdrawal functionality | 2025-12-12 | 2025-12-12 | Navya N | Development | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0
US-04 | T-10 | Implement fund transfer logic | 2025-12-15 | 2025-12-16 | Navya N | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US-04 | T-11 | Validate transaction rules | 2025-12-17 | 2025-12-17 | Navya N | Testing | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 3 BACKLOG
US-05 | T-12 | Create custom exception classes | 2025-12-18 | 2025-12-18 | uppari Mounika | Development | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US-05 | T-13 | Integrate exception handling in services | 2025-12-19 | 2025-12-22 | Uppari Mounika | Development | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
US-06 | T-14 | Implement low balance alert logic | 2025-12-23 | 2025-12-24 | Riya Kumari | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
US-06 | T-15 | Configure email notification utility | 2025-12-26 | 2025-12-26 | Riya Kumari | Testing | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SPRINT 4 BACKLOG
US-07 | T-16 | Design UI screens for banking operations | 2025-12-29 | 2025-12-30 | Navya N | UI Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US-07 | T-17 | Connect UI with service layer | 31-Dec-25 | 2025-12-31 | Navya N | Integration | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
US-08 | T-18 | Perform end-to-end testing | 2026-01-02 | 8-Jan-26 | Navya N | Testing | In Progress | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | JDK version compatibility issue during setup | Installed compatible JDK version and updated environment variables
Sprint 1 | Day 2 | Maven dependencies not resolving properly | Updated Maven settings and reloaded dependencies
Sprint 1 | Day 4 | Uncertainty in defining account attributes | Reviewed requirements and finalized Account model fields
Sprint 2 | Day 8 | Incorrect balance calculation logic | Debugged service logic and corrected conditional checks
Sprint 2 | Day 10 | Validation failing for insufficient balance | Added proper validations and exception handling
Sprint 2 | Day 12 | Delay in testing transaction scenarios | Created test cases and completed transaction testing
Sprint 3 | Day 14 | Email alert not triggering as expected | Verified SMTP configuration and fixed EmailUtil logic
Sprint 4 | Day 18 | Minor issues during API integration | Debugging API calls and performing end-to-end testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-01 | 2025-12-07 | Navya N | Planning tasks before starting implementation | Rushing directly into coding | Following proper project structure | Prepared a clear setup checklist before development
2 | Sprint 2 | 2025-12-08 | 2025-12-17 | Navya N | Writing validations along with business logic | Skipping edge case handling | Modular service-based design | Added validation checks in transaction services
3 | Sprint 3 | 2025-12-18 | 2025-12-26 | Navya N | Handling exceptions in a centralized manner | Hard-coding values inside services | Using reusable utility classes | Implemented custom exceptions and improved error flow
4 | Sprint 4 | 2025-12-29 | 2026-01-02 | Navya N | Testing APIs incrementally during integration | Delaying testing until end | End-to-end testing approach | Started testing APIs along with UI integration
5 | Sprint 4 | 2025-12-29 | 2026-01-02 | Navya N | Improving UI usability based on test results | Mixing UI and business logic | Clean separation of layers | Refactored code to keep UI and service logic separate
6 | Sprint 4 | 2025-12-29 | 2026-01-02 | Navya N | Documenting API behaviour clearly | Ignoring documentation during development | Maintaining code comments | Updated documentation alongside API development
7 | Sprint 4 | 2025-12-29 | 2026-01-02 | Navya N | Reviewing code after each feature | Leaving unused code in project | Writing clean and readable code | Removed unused code and refactored classes